## Slide 1: Cuyahoga County Airport Runway 6/24 Safety Area Improvement Program OVERVIEW September 2015

## Slide 2: Multi-Year Program Overview
  Runway “shift” to the west
  Reconstruct 1,239’ of the Runway 6 end 1,002’ of the Runway 24 end
  Install new drainage & grade RSA to standards (+/- 500,000 CY of cut)
  Reconstruct southern half of existing Runway 6/24
  Rehabilitate northern half of existing Runway 6/24
  Edge Lights – Raise and Relocate
  322’ EMAS bed on Runway 6 departure end
  435’ EMAS bed on Runway 24 departure end
  Relocate Runway 24 approach lights
  Relocate Runway 24 Glideslope antenna & PAPI

## Slide 3: Why?
  Non-compliant Runway Safety Area (RSA) off ends of the Runway 6/24
  Runway lateral RSA grades not compliant
  Ground within primary surface & Part 77 transitional surface
  Inadequate pavement section
  Non-complaint transverse grades on Runway (super elevated)
  Non-complaint connector taxiway location (direct access from apron to runway w/o turn)

## Slide 4: Why?

## Slide 5: Why?

## Slide 6: What are the project limitations?
  FAA Funding
    Timing (normally do not issue grants until September)
    Discretionary Amount(s) Unknown
    FY 15 is last year of the 4-year Reauthorization Bill
  Can’t start on the runway ends first
    Shorten existing runway
    Profile issues
  No work within the RSA when runway is open
  FAA will not grant modifications to standards on runway transverse grades

## Slide 7: Overall Phasing Schedule
  Package #1 – Earthwork & Drainage - $5 M
    Received Bids - June 2015
    Grant Issued – September 2015
    Construction – March 2016
  Package #2 – Reconstruct/Rehabilitate Existing Runway 6/24 - $9.8M
    Receive Bids – April 2016
    Construction – August 2016 – November 2016
  Package #3 – Runway 6 End Reconstruction/Shift/EMAS Installation - $10M
    Construction – March 2017
  Package #4 – Runway 24 End Reconstruction/Shift/EMAS Installation - $15M
    Construction – March 2018

## Slide 8: Package #1 – Earthwork & Drainage
  \

## Slide 9: Package #2 – Existing Runway 6/24 Rehabilitation/Reconstruction

## Slide 10: Project #3 – Runway 6 End Extension & EMAS

## Slide 11: Project #4 – Runway 24 End Relocation & EMAS

## Slide 12: Project Completion
  Compliant RSA
  Pavement Section // 20-year design life
  Complaint ROFA and Part 77 Primary Surface
  Standard runway transverse grades
  Compliant taxiway connector locations
  Final Declared Distances
    5,502’
    Runway 24 LDA – 5,000’
    Runway 6 LDA – 5,184’